## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sai Pavan Reddy | 2026-02-10 | OCR output not extracting full address from Aadhaar image | Sprint 1 | Backend Team | Functional | Improved preprocessing and added Tesseract config for multi-line extraction | 2026-02-11 | Closed | Verified successfully
2 | Aishmi Anish | 2026-02-23 | Model output returning inconsistent address verification scores | Sprint 2 | Backend Team | Algorithmic | Adjusted threshold values and retrained model | 2026-02-24 | Closed | Performance improved
3 | Devansh Gupta | 2026-02-25 | Frontend not displaying fraud prediction results correctly | Sprint 2 | Frontend Team | UI/Integration | Fixed JSON parsing and updated API endpoint in React | 2026-02-26 | Closed | Tested and verified
4 | Gayatri Mohture | 2026-02-27 | GNN model showing NaN values during training | Sprint 2 | Backend Team | Model Training | Normalized data and fixed null entries in graph edges | 2026-02-28 | Closed | Stable model output
5 | Sai Pavan Reddy | 2026-03-09 | AML check module failing on duplicate address input | Sprint 3 | Backend Team | Logic | Added address hashing and duplicate detection rule | 2026-03-10 | Closed | Verified via testing
6 | Aishmi Anish | 2026-03-11 | Upload form not handling invalid file formats | Sprint 3 | Frontend Team | UI/Validation | Added MIME type check and error popup | 2026-03-12 | Closed | User-friendly validation added
7 | Devansh Gupta | 2026-03-13 | Real-time pipeline response delay | Sprint 3 | Backend Team | Performance | Implemented async processing and caching | 2026-03-14 | Closed | Latency reduced by 35%
8 | Gayatri Mohture | 2026-03-23 | Dashboard graphs not updating after backend changes | Sprint 4 | Frontend Team | Integration | Re-linked data binding with new API route | 2026-03-24 | Closed | Graph sync issue resolved
9 | Sai Pavan Reddy | 2026-03-25 | Fraud alerts not showing in admin view | Sprint 4 | Backend Team | Functional | Fixed alert trigger logic in API | 2026-03-26 | Closed | Verified
10 | Aishmi Anish | 2026-03-27 | Minor typo and alignment issues in UI | Sprint 4 | Frontend Team | UI | Adjusted CSS layout and corrected labels | 2026-03-28 | Closed | Presentation-ready